YOUTUBE CHANNEL STRATEGY FinEdge India ¦ Personal Finance & Investing ¦ 90-Day Channel Growth Plan Internship Project — Content Strategy & Channel Management

1. Executive Summary

This document presents a comprehensive 90-day YouTube Channel Strategy for FinEdge India, a personal finance and investing education brand targeting young working professionals and college students across India. With over 500 million YouTube users in India and a rapidly growing appetite for financial literacy content, YouTube represents the single most powerful platform for FinEdge India to build trust, grow an audience, and establish long-term brand authority in the competitive but underserved Hindi and English personal finance space.

The strategy covers every dimension of channel success: full channel setup and optimisation, a four-pillar content framework, 90-day phased growth plan, video SEO mastery, production workflow, audience engagement systems, monetisation roadmap, and weekly KPI tracking. The plan is anchored in three core principles — consistency over virality, search-first content thinking, and delivering genuine financial value to every viewer who clicks play.

2. Channel Overview

| Channel Name | FinEdge India |
| --- | --- |
| Channel Handle | @FinEdgeIndia |
| Brand / Organisation | FinEdge India Pvt. Ltd. (EdFinTech Startup) |
| Channel Category | Personal Finance, Investing & Financial Literacy |
| Primary Goal | Build a loyal subscriber base of financially curious Indians aged 18–35 and establish FinEdge as a trusted money education brand |
| Target Audience | College students and working professionals aged 18–35 in Tier-1 & Tier-2 Indian cities seeking practical money management guidance |
| Strategy Duration | 90 Days (Phase 1: Days 1–30 ¦ Phase 2: Days 31–60 ¦ Phase 3: Days 61–90) |
| Upload Frequency | 2 long-form videos per week (Tuesday & Friday) + 1 YouTube Short per week |
| Language | Primary: English; Bilingual (Hindi-English) for Shorts and regional audience growth |
| 90-Day Benchmark | 500 subscribers, 3,000 watch-hours, average CTR above 5%, and AVD above 45% |

3. Channel Setup & Optimisation

Before a single video is published, every element of the FinEdge India channel must be fully optimised. YouTube’s algorithm uses channel-level signals — name, keywords, description, links — as ranking inputs. A polished, complete channel converts casual visitors into subscribers within seconds.

| Element | Requirement | FinEdge India Best Practice |
| --- | --- | --- |
| Channel Name | Clear, searchable, brand-consistent | FinEdge India — immediately communicates niche (finance) and geography (India) |
| Channel Handle | Unique @handle, identical across platforms | @FinEdgeIndia — consistent on Instagram, LinkedIn, and Twitter for cross-platform discovery |
| Channel Art | 2560×1440 px banner | Show upload schedule (Tue & Fri), tagline ‘India ka Financial Mentor’, and social handles |
| Profile Picture | 800×800 px high-contrast logo | FinEdge India logo on white background — clean, professional, recognisable at 98px thumbnail size |
| Channel Description | 1,000 chars max, keyword-rich | Open with: ‘Learn how to save, invest, and grow your money — simple finance for every Indian.’ Include keywords: personal finance India, investing for beginners, mutual funds, SIP, stock market |
| Channel Trailer | 60–90 sec hook for non-subscribers | Hook: ‘Most Indians earn well but never build wealth — here’s why, and here’s how to fix it in 5 steps.’ End with clear subscribe CTA |
| Featured Sections | Organise homepage by content series | Pin: ‘Investing 101 for Beginners’ playlist, Latest Uploads, and ‘Fix Your Finances in 30 Days’ series |
| Links & Socials | Up to 14 links on channel page | Link to FinEdge India website, free budget template download, Instagram, and LinkedIn |

4. Content Pillars

All FinEdge India videos map to one of four content pillars. This framework ensures variety without randomness — every upload serves a clear audience need and a measurable strategic purpose:

Educate (35%) (35%) How SIP works, mutual fund basics, income tax explained, emergency fund guide, credit score 101. Highest search intent — drives organic traffic and long-term watch time.

Inspire (25%) (25%) How a ₹5,000/month SIP became ₹50 lakhs, young Indians who retired early, real salary breakdown case studies. Drives shares, saves, and emotional connection.

Entertain (25%) (25%) Finance myths busted, reacting to bad money advice, ‘rate my budget’ audience segments, day-in-the-life of a young investor. Drives comments, likes, and community growth.

Convert (15%) (15%) Best apps for investing in India, Zerodha vs Groww comparison, top index funds for 2025, affiliate product reviews. Drives clicks, app sign-ups, and affiliate revenue.

5. 90-Video Ideas Bank (First 45 Days)

Every video title below is keyword-researched and mapped to a content pillar. Titles follow the proven YouTube formula: number or power word + primary keyword + benefit or curiosity hook:

| # | Video Title | Pillar |
| --- | --- | --- |
| 1 | How to Start a SIP in India in 2025 — Complete Beginner’s Guide | Educate |
| 2 | I Invested ₹3,000/Month for 5 Years — Here’s What Happened | Inspire |
| 3 | 7 Money Mistakes Every Indian Makes in Their 20s (and How to Fix Them) | Educate |
| 4 | Zerodha vs Groww vs Angel One — Which is Best for Beginners in 2025? | Convert |
| 5 | How to Build an Emergency Fund on a ₹25,000 Salary | Educate |
| 6 | Indian Finance Myths That Are Keeping You Poor (Reaction) | Entertain |
| 7 | What is an Index Fund? The Simplest Explanation for Indians | Educate |
| 8 | Real Budget Breakdown: How Priya (Age 24, ₹40K Salary) Saves 40% Every Month | Inspire |
| 9 | Income Tax for Beginners India 2025 — Old Regime vs New Regime Explained Simply | Educate |
| 10 | Best Mutual Funds to Start With in India (Under ₹500/Month) | Convert |
| 11 | How I Would Invest ₹10,000 Today if I Were Starting from Zero | Inspire |
| 12 | Credit Score 101: What It Is, Why It Matters, and How to Fix a Bad One | Educate |

6. 90-Day Phased Channel Growth Plan

Phase 1 — Foundation (Days 1–30): Set Up, Research & Launch FinEdge India

No uploads until the channel is fully optimised and a content bank of at least 8 videos is ready. In the personal finance niche, credibility begins before the first subscriber.

- Complete full FinEdge India channel setup: name, handle, art, description, channel trailer, featured sections, and all linked social profiles

- Conduct YouTube keyword research using TubeBuddy and VidIQ: identify 25 high-volume, low-competition keywords in the Indian personal finance space (e.g. ‘SIP for beginners India’, ‘how to save money in India’, ‘mutual funds India 2025’)

- Analyse top 10 competing Indian finance channels (e.g. Pranjal Kamra, CA Rachana Ranade, Labour Law Advisor): study thumbnails, title formulas, best-performing videos, and comment sections for audience pain points

- Plan first 12 video topics mapped to researched keywords across all 4 content pillars; assign each a pillar, keyword, estimated search volume, and difficulty score

- Film and edit a content bank of 8 videos before publishing the first upload — this ensures consistency even during high-workload weeks

- Design 5 FinEdge India thumbnail templates in Canva: dark red background, bold white text (max 5 words), Rupee symbol accents, and consistent face placement in the right third

- Publish Video 1 (‘How to Start a SIP in India in 2025’) with full SEO: keyword-rich title, 400+ word description, 12 tags, end screens, info cards, and timestamped chapters

Phase 2 — Growth (Days 31–60): Publish Consistently & Optimise Every Video

Maintain the 2 videos/week cadence. After every upload, study the data and iterate. In the finance niche, trust builds through consistency and accuracy.

- Publish Videos 5–14 on schedule; cross-promote every upload on Instagram Reels (30-second clip of the best insight), LinkedIn (written post summarising the video’s top 3 takeaways), and relevant WhatsApp finance groups

- Review YouTube Studio analytics every Monday: CTR, Average View Duration, Impressions, Traffic Sources, and the Audience Retention graph to identify the exact moment viewers drop off

- A/B test thumbnails on the top 3 performing videos using YouTube’s thumbnail test feature — test one variable at a time (text vs no text, face vs no face, different colours)

- Respond to every comment within 24 hours — pin the most insightful question from each video and answer it publicly to encourage further engagement

- Publish 3 community posts per week: a finance poll (‘Do you have a budget?’), a quick money tip, and a preview of the upcoming video

- Identify the 3 best-performing Phase 1 videos by watch time and CTR; create follow-up or companion videos for each to capture existing audience momentum

- Pitch 2 collaboration videos with adjacent Indian creators in career, productivity, or student life niches — cross-promotion is the fastest organic growth lever on YouTube

Phase 3 — Scale (Days 61–90): Systematise, Monetise & Plan Quarter 2

Build repeatable systems so FinEdge India’s content engine runs beyond the 90-day sprint. Explore monetisation and establish the channel as a recognised name in Indian financial education.

- Review the full 60-day analytics report: identify top 3 content formats, best publishing times (Tuesday vs Friday performance comparison), and highest-retention video structures

- Refine the content strategy based on data — shift budget towards pillars with demonstrated audience traction; reduce output in underperforming categories

- Apply for YouTube Partner Programme (YPP) once 500 subscribers and 3,000 watch-hours are achieved; enable ads revenue on all eligible videos

- Launch FinEdge India’s first YouTube Live: a 45-minute ‘Ask Me Anything — Your Money Questions Answered’ session to deepen community trust and boost watch time significantly

- Build a Shorts strategy: repurpose the single best 45-second insight from every long-form video into a YouTube Short — Shorts can surface the channel to an entirely new algorithmic audience

- Document the FinEdge India Content SOP: research → keyword validation → scripting → filming → editing → thumbnail design → SEO upload → cross-promotion → analytics review

- Compile the full 90-day performance report with channel metrics, top-performing videos, audience insights, and a strategic content plan for Quarter 2

7. Video SEO Framework

YouTube is India’s second-largest search engine after Google. Every FinEdge India video must be fully optimised to rank for the financial queries its audience is actively searching:

| SEO Element | FinEdge India Best Practice | Why It Matters |
| --- | --- | --- |
| Video Title | Start with primary keyword; use numbers; keep under 60 characters. Example: ‘How to Start SIP in 2025 — Complete India Guide’ | Highest-weight ranking signal; determines CTR in YouTube and Google search results |
| Description | First 3 lines: keyword + value proposition (visible before ‘show more’). Add timestamps, 3 related video links, social links, disclaimer | Crawled by YouTube and Google for indexing; descriptions above 300 words rank meaningfully better |
| Tags | Use 12–15 tags: exact keyword, long-tail variations (‘SIP for beginners India 2025’), and broad niche (‘personal finance India’, ‘investing’) | Helps YouTube understand topic context; still a supporting signal despite reduced standalone weight |
| Thumbnail | 1280×720 px; bold 4-word max text; dark red or white background; Rupee sign as visual anchor; consistent face placement | Directly controls CTR — the single most impactful element; test all thumbnails after 48 hours |
| Chapters | Timestamp every 2–3 minutes with keyword-rich labels e.g. ‘0:00 What is a SIP ¦ 2:30 How Much to Invest ¦ 5:00 Best SIP Apps’ | Indexes in Google Search as video chapters; improves user experience and average view duration |
| End Screens | Add 20–25 sec from end: 1 related video + 1 subscribe button; avoid cluttering with 4+ elements | Keeps viewers in the FinEdge India ecosystem; directly reduces session bounce rate |
| Info Cards | Add at peak engagement moments (40–60% into video) linking to a related FinEdge India video or playlist | Boosts internal watch time and playlist completion; signals channel authority to the algorithm |
| Auto Captions | Generate auto-captions and manually correct finance-specific terms (SIP, ELSS, LTCG, NAV) — add keyword phrases | Indexes every spoken word; improves accessibility and average session duration significantly |

8. Content Production Workflow

Every FinEdge India video follows a 7-stage production pipeline. Repeatable processes are what separate channels that grow from channels that burn out:

| Stage | FinEdge India Activity | Tools Used |
| --- | --- | --- |
| 1. Research | Validate keyword search volume; study top 3 ranking videos; extract audience questions from comments | TubeBuddy, VidIQ, Google Trends, YouTube Search |
| 2. Scripting | Write full script with hook in first 30 seconds; include a ‘stay for this’ mid-video retention hook; end with CTA | Google Docs, Notion; SEBI compliance check for any investment claims |
| 3. Filming | Talking-head setup with clean financial chart B-roll; minimal background; lapel or shotgun mic for audio clarity | Smartphone (4K) or DSLR, Rode Wireless GO mic, ring light, green screen for data overlays |
| 4. Editing | Hard cuts every 4–5 seconds; animated text overlays for key numbers (₹ amounts, %, timelines); intro ≤15 sec | DaVinci Resolve (free), CapCut for Shorts; Motion Array for templates |
| 5. Thumbnail | Design 2 variants per video; A/B test after 48 hours; optimise the underperforming variant within 1 week | Canva Pro, Adobe Express |
| 6. SEO & Upload | Write keyword-rich title, 400-word description, tags, chapters; schedule for 8 AM IST Tuesday or Friday | YouTube Studio, TubeBuddy tag explorer |
| 7. Promote | 30-sec Reel clip → Instagram; 3 takeaways post → LinkedIn; Shorts version → YouTube; share in personal finance WhatsApp communities | Instagram, LinkedIn, WhatsApp, Reddit r/IndiaInvestments |

9. Sample Weekly Content Calendar (Week 6)

A typical week during the active growth phase of the FinEdge India 90-day strategy:

| Day | Activity | Detail |
| --- | --- | --- |
| Monday | Research & scripting | Keyword research for Week 7 videos; write full script for ‘Best Index Funds India 2025’; SEBI compliance check |
| Tuesday | Publish Video 11 | Upload ‘How I Would Invest ₹10,000 Today’; full SEO; schedule for 8 AM IST; post 30-sec Reel clip on Instagram |
| Wednesday | Filming day | Film both Week 7 videos back-to-back; record a 45-sec Short from Tuesday’s best insight (‘The 50-30-20 Rule Explained in Hindi’) |
| Thursday | Editing & thumbnail design | Edit both Week 7 videos; design 2 thumbnail variants each in Canva; reply to all Tuesday video comments |
| Friday | Publish Video 12 | Upload ‘Credit Score 101 India’; full SEO; community post with poll — ‘Do you know your credit score?’ |
| Saturday | Analytics review | Review CTR, AVD, impressions, subscriber gain for the week; identify retention drop-off points in both videos |
| Sunday | Publish YouTube Short + plan | Upload Wednesday’s Short; LinkedIn written post summarising Week’s top money insight; plan Week 8 topics |

10. Content Voice & Scripting Guide

FinEdge India’s voice must feel like a knowledgeable friend who explains money without jargon, without fear-mongering, and without oversimplifying the real stakes.

Hook in the first 30 seconds — no exceptions Do: "If you have a salary and no investments yet, you are losing money every single day — not because you spend too much, but because of something called inflation erosion. By the end of this video, you will know exactly how to fix it in under 20 minutes." Avoid: NOT: "Hey guys! Welcome back to FinEdge India! Today we are going to talk about investing, so let’s get started. But first, please like and subscribe!"

Specific numbers, not vague advice Do: "A ₹5,000 SIP in a Nifty 50 index fund started at age 22 becomes approximately ₹3.2 crore by age 60 at a 12% CAGR. The same SIP started at 32 gives you only ₹1.1 crore. That 10-year delay costs you ₹2.1 crore." Avoid: NOT: "Starting early in your investments makes a huge difference because of compound interest, so you should really start as soon as possible."

Compliance-aware, not reckless Do: "This is for educational purposes only — please consult a SEBI-registered advisor before making any investment decisions. What I can do is show you how the maths works." Avoid: NOT: "Just buy this fund, it gives great returns" or making specific buy/sell recommendations without SEBI registration.

11. KPIs & Success Metrics

The following KPIs will be reviewed every Monday in YouTube Studio throughout the FinEdge India 90-day strategy:

| Metric | Target / Benchmark | Review Frequency |
| --- | --- | --- |
| Subscriber Growth | 500 subscribers by Day 90 (YouTube Partner Programme eligibility) | Weekly |
| Watch Hours | 3,000 watch-hours by Day 90 (2024 YPP threshold for basic monetisation) | Weekly |
| Click-Through Rate (CTR) | Target 5–8% average; below 3.5% = thumbnail A/B test required immediately | Per Video |
| Average View Duration (AVD) | Minimum 45% of total video length; above 55% signals excellent audience retention | Per Video |
| Impressions | Track weekly growth — rising impressions = algorithm is actively distributing content | Weekly |
| Comment Rate | Reply to 100% of comments in first 48 hours; aim for 0.5%+ comment-to-view ratio | Daily |
| Shorts Views | Each Short to reach 1,000+ views within 72 hours; Shorts feed new audiences | Per Short |
| Affiliate Link Clicks | Track clicks on Groww / Zerodha affiliate links in description using Bitly UTM | Weekly |

12. Monetisation Roadmap

FinEdge India’s monetisation strategy is built in layers — starting with affiliate income from Day 1 and scaling towards ads, memberships, and digital products as the channel grows:

| Phase | Revenue Stream | Requirement / Notes |
| --- | --- | --- |
| Day 1+ | Affiliate marketing — Groww, Zerodha, INDmoney | No subscriber threshold; add referral links to every video description immediately; disclose per SEBI guidelines |
| Day 1+ | Brand sponsorships — fintech apps, insurance, credit cards | Accessible from 500+ subscribers for niche finance channels; disclose all paid partnerships clearly |
| Day 60+ | YouTube Partner Programme — ad revenue on all videos | 500 subscribers + 3,000 watch-hours (2024 basic YPP threshold); enable on all monetisation-eligible videos |
| Day 75+ | Channel memberships — exclusive finance Q&A sessions | 1,000 subscribers required; offer 3 membership tiers (₹49, ₹149, ₹499) with escalating benefits |
| Day 90+ | Digital products — budget template, SIP calculator, finance course | Any subscriber count; host on Gumroad or Teachable; promote through end screens and community posts |
| Ongoing | Consulting & speaking — inbound from channel authority | Positions FinEdge India as a credible brand in the Indian financial education ecosystem |

13. Conclusion

This 90-day YouTube Channel Strategy positions FinEdge India to build genuine, lasting authority in India’s fast-growing financial literacy space. India has one of the world’s youngest populations, a massive under-invested middle class, and a generation of digital natives hungry for practical, honest money education in their own language and context. FinEdge India is designed to meet exactly that need — on the world’s biggest video platform.

The phased approach ensures that Phase 1’s research and setup investments pay dividends in every Phase 2 upload, and that Phase 2’s data directly sharpens Phase 3’s strategy. By prioritising CTR, Average View Duration, and watch time over raw subscriber vanity metrics, FinEdge India builds a channel the algorithm actively rewards — one that keeps growing long after the 90-day sprint concludes.

Every FinEdge India viewer who learns something actionable — starts a SIP, builds an emergency fund, files taxes correctly for the first time — is proof that content-driven financial education at scale is not just a business model; it is a genuine public good. That mission is what makes FinEdge India worth building right.